Business Continuity Plan

Copilot Studio Implementation

Project Plan & Timeline

Date: November 23, 2025

Duration: 8-10 weeks

Team Size: 3-4 people

Project Overview

Scope: Implementation of Copilot Studio solution for Business Continuity Plan document Q&A

Documents: ~50 documents across multiple SharePoint sites with folder hierarchies

Key Objectives:

• Enable natural language Q&A for BCP documents

• Maintain existing SharePoint security and permissions

• Provide fast, accurate responses with proper citations

• Ensure enterprise-grade compliance and governance

Team Structure

• Copilot Studio Developer (1)

• SharePoint Administrator (1)

• BCP Subject Matter Expert (1)

• Project Manager (1)

Project Gantt Chart

| Phase | Task | Days | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 1 | SharePoint Audit | 3 |  |  |  |  |  |  |  |  |  |  |
|  | Permission Analysis | 2 |  |  |  |  |  |  |  |  |  |  |
|  | Licensing Setup | 1 |  |  |  |  |  |  |  |  |  |  |
|  | Stakeholder Interviews | 3 |  |  |  |  |  |  |  |  |  |  |
|  | Success Metrics | 1 |  |  |  |  |  |  |  |  |  |  |
|  | Architecture Design | 2 |  |  |  |  |  |  |  |  |  |  |
| Phase 2 | Create Environment | 0.5 |  |  |  |  |  |  |  |  |  |  |
|  | SharePoint Connector | 2 |  |  |  |  |  |  |  |  |  |  |
|  | Document Indexing | 1.5 |  |  |  |  |  |  |  |  |  |  |
|  | Test Connectivity | 1 |  |  |  |  |  |  |  |  |  |  |
| Phase 3 | Base Gen AI Topic | 2 |  |  |  |  |  |  |  |  |  |  |
|  | Conversation Flows | 3 |  |  |  |  |  |  |  |  |  |  |
|  | Document Citations | 1.5 |  |  |  |  |  |  |  |  |  |  |
|  | Content Moderation | 1 |  |  |  |  |  |  |  |  |  |  |
|  | Error Handling | 1.5 |  |  |  |  |  |  |  |  |  |  |
| Phase 4 | Internal Testing | 2 |  |  |  |  |  |  |  |  |  |  |
|  | Permission Testing | 2 |  |  |  |  |  |  |  |  |  |  |
|  | Pilot User Testing | 5 |  |  |  |  |  |  |  |  |  |  |
|  | Quality Refinement | 3 |  |  |  |  |  |  |  |  |  |  |
|  | Performance Testing | 1 |  |  |  |  |  |  |  |  |  |  |
| Phase 5 | Production Environment | 0.5 |  |  |  |  |  |  |  |  |  |  |
|  | Teams/Intranet Integration | 2 |  |  |  |  |  |  |  |  |  |  |
|  | Documentation | 2 |  |  |  |  |  |  |  |  |  |  |
|  | Training Sessions | 2 |  |  |  |  |  |  |  |  |  |  |
|  | Phased Rollout | 1 |  |  |  |  |  |  |  |  |  |  |
| Phase 6 | Monitor Analytics | Ongoing |  |  |  |  |  |  |  |  |  |  |
|  | User Support | 5 |  |  |  |  |  |  |  |  |  |  |
|  | Iterative Improvements | 3 |  |  |  |  |  |  |  |  |  |  |
|  | Refresh Process Setup | 1 |  |  |  |  |  |  |  |  |  |  |
|  | Final Report | 1 |  |  |  |  |  |  |  |  |  |  |

Legend:

Blue = Discovery & Planning  |  Green = Environment Setup  |  Orange = Development

Purple = Testing  |  Red = Deployment  |  Cyan = Post-Launch Support

Detailed Project Plan

Phase 1: Discovery & Planning (Week 1-2)

| Task ID | Task Name | Duration | Dependencies | Effort Justification |
| --- | --- | --- | --- | --- |
| 1.1 | SharePoint Site & Document Audit | 3 days | None | • Catalog all 50 documents across sites • Identify folder structures • Coordinate with site owners • Document access patterns |
| 1.2 | Permission & Security Analysis | 2 days | 1.1 | • Map permission groups • Identify sensitive classifications • Ensure compliance • Test permission inheritance |
| 1.3 | Copilot Studio Licensing Setup | 1 day | None | • Verify licenses • Request additional if needed • Set up dev environment • Handle procurement |
| 1.4 | Stakeholder Interviews | 3 days | None | • Interview 8-10 team members • Understand common questions • Document pain points • Prioritize features |
| 1.5 | Success Metrics Definition | 1 day | 1.4 | • Define success criteria • Establish baseline metrics • Set adoption targets • Create tracking mechanisms |
| 1.6 | Technical Architecture Design | 2 days | 1.1, 1.2, 1.3 | • Design data source connections • Plan error handling • Determine integration points • Document security approach |

Phase 2: Environment Setup & Configuration (Week 3)

| Task ID | Task Name | Duration | Dependencies | Effort Justification |
| --- | --- | --- | --- | --- |
| 2.1 | Create Copilot Studio Environment | 0.5 day | 1.6 | • Set up dev environment • Configure basic settings • Straightforward process • Requires careful configuration |
| 2.2 | SharePoint Connector Configuration | 2 days | 2.1, 1.1 | • Connect to multiple sites • Configure OAuth/service account • Test connectivity • Troubleshoot permissions |
| 2.3 | Document Indexing Setup | 1.5 days | 2.2 | • Configure folders to index • Set up refresh schedules • Exclude non-relevant files • Initial indexing takes time |
| 2.4 | Test Data Source Connectivity | 1 day | 2.3 | • Verify document access • Test different permission levels • Validate folder hierarchy • Document issues |

Phase 3: Copilot Development (Week 4-5)

| Task ID | Task Name | Duration | Dependencies | Effort Justification |
| --- | --- | --- | --- | --- |
| 3.1 | Create Base Generative Answers | 2 days | 2.4 | • Configure AI model settings • Prompt engineering for BCP • Define response format • Test with sample queries |
| 3.2 | Design Conversation Flow | 3 days | 3.1, 1.4 | • Create guided topics • Design conversation trees • Build fallback mechanisms • Multiple iterations needed |
| 3.3 | Implement Document Citation | 1.5 days | 3.1 | • Configure citation format • Include SharePoint links • Test user access to sources • Format for readability |
| 3.4 | Content Moderation & Filters | 1 day | 3.1 | • Set up moderation policies • Configure PII detection • Test with edge cases • Ensure compliance |
| 3.5 | Error Handling & Fallback | 1.5 days | 3.2 | • Design unanswerable responses • Create escalation paths • Handle connectivity issues • Test failure scenarios |

Phase 4: Testing & Refinement (Week 6-7)

| Task ID | Task Name | Duration | Dependencies | Effort Justification |
| --- | --- | --- | --- | --- |
| 4.1 | Internal Testing | 2 days | 3.5 | • Test 30-50 BCP questions • Verify response accuracy • Check citation correctness • Document issues |
| 4.2 | Permission Testing | 2 days | 4.1 | • Test different access levels • Verify authorized content only • Test edge cases • Multiple test accounts |
| 4.3 | Pilot User Group Testing | 5 days | 4.2 | • Select diverse pilot group • Provide training • Collect feedback over 3-5 days • Real scenario testing needed |
| 4.4 | Response Quality Refinement | 3 days | 4.3 | • Analyze pilot feedback • Adjust prompt engineering • Improve topic flows • Iterative refinement |
| 4.5 | Performance & Load Testing | 1 day | 4.4 | • Test concurrent users • Verify response times • Check indexing refresh • Identify bottlenecks |

Phase 5: Deployment & Rollout (Week 8)

| Task ID | Task Name | Duration | Dependencies | Effort Justification |
| --- | --- | --- | --- | --- |
| 5.1 | Create Production Environment | 0.5 day | 4.5 | • Clone dev to prod • Verify all connections • Quick but careful validation • Production settings |
| 5.2 | Integration with Teams/Intranet | 2 days | 5.1 | • Deploy as Teams app • Add to intranet if needed • Configure SSO • Test integrations |
| 5.3 | User Documentation | 2 days | 4.5 | • Create user guide • Develop quick reference • Record demo video • Prepare FAQ |
| 5.4 | Conduct Training Sessions | 2 days | 5.3 | • Schedule 2-3 sessions • Live demos and Q&A • Hands-on practice • Record for reference |
| 5.5 | Phased Rollout to Full Team | 1 day | 5.2, 5.4 | • Grant access in waves • Monitor for issues • Provide initial support • Collect early feedback |

Phase 6: Post-Launch Support & Optimization (Week 9-10)

| Task ID | Task Name | Duration | Dependencies | Effort Justification |
| --- | --- | --- | --- | --- |
| 6.1 | Monitor Usage & Analytics | Ongoing | 5.5 | • Daily monitoring 2 weeks • Track adoption metrics • Identify problem queries • Continuous activity |
| 6.2 | User Support & Issue Resolution | 5 days | 5.5 | • Respond to user questions • Fix bugs and issues • Provide helpdesk support • Higher initial load |
| 6.3 | Iterative Improvements | 3 days | 6.1 | • Analyze common queries • Add new topics • Improve low-confidence responses • Optimize flows |
| 6.4 | Document Refresh Process | 1 day | 6.1 | • Process for new documents • Configure change alerts • Test refresh/reindexing • Create maintenance runbook |
| 6.5 | Final Report & Handoff | 1 day | 6.3, 6.4 | • Compare to success metrics • Document lessons learned • Create maintenance guide • Handoff to operations |

Risk Management & Mitigation

| Risk | Impact | Probability | Mitigation Strategy |
| --- | --- | --- | --- |
| SharePoint Permission Complexity | High | Medium | • Add 2-3 days buffer to Phase 1-2 • Early permission testing • Engage SharePoint admin early • Document permission structure thoroughly |
| Licensing Procurement Delays | High | Medium | • Start licensing request in Week 1 • Identify procurement lead time • Have backup approval path • Can add 1-2 weeks to timeline |
| Pilot Feedback Requires Major Changes | Medium | Medium | • Select representative pilot group • Set clear expectations • May extend Week 6-7 by 3-5 days • Prioritize critical feedback |
| Document Quality Issues | Medium | Low | • Identify during Phase 1 audit • May need document cleanup (add 1 week) • Work with content owners • Use OCR if needed for scans |
| User Adoption Challenges | Medium | Low | • Comprehensive training program • Champions/advocates approach • Collect and act on feedback quickly • Show quick wins early |

Success Criteria & KPIs

| KPI Category | Metric | Target |
| --- | --- | --- |
| User Adoption | Active users in first month | 80% of BCP team |
| Response Quality | User satisfaction rating | 4.0+ out of 5.0 |
| Efficiency Gain | Time saved per query vs manual search | 70% reduction (5 min → 1.5 min) |
| Accuracy | Correct answers with proper citations | 85%+ accuracy rate |
| Performance | Average response time | < 5 seconds per query |

Immediate Next Steps

1. Secure Executive Approval

• Present project plan to leadership

• Obtain budget approval

• Confirm resource allocation

2. Initiate Licensing Process (CRITICAL)

• Verify current Copilot Studio licenses

• Submit procurement request for additional licenses

• Identify lead time for license activation

3. Assemble Project Team

• Assign Project Manager

• Identify Copilot Studio Developer

• Engage SharePoint Administrator

• Designate BCP Subject Matter Expert

4. Schedule Kickoff Meeting

• Set project start date

• Align team calendars

• Review project plan with team

5. Begin Phase 1 Activities

• Start SharePoint site audit

• Schedule stakeholder interviews

• Initiate licensing setup